Introduction to Software Engineering

Weekly Status Report

The student team is required to complete the Weekly Status Report documentation for the assigned course project, following the attached template.

Software Engineering Department

Faculty of Information and Technology

University of Science

Table of Contents

Objectives	1

1 Report Information	2

1.1 Task Status	2

1.2 Plan for Next Week	3

1.3 Issues and Risks	4

1.4 Meeting Minutes	4

1.5 Metrics	4

Weekly Status Report

# Objectives

This document focus on the following topics:

- Reporting weekly progress against the project plan

- Recording issues and risks

- Recording the weekly status meet

# Report Information

| Item | Value |
| --- | --- |
| Team | No pain no gain - T08 |
| Week | 04 |
| Date of meeting | 24/10/2026 & 28/10/2026 |
| Current phase / PA | PA2 |
| Prepared by | Lê Trọng Hiếu & Trần Duy Khang |
| Overall status |  |

## Task Status

| WBS / task | Owner | Planned finish | Status | % done | Notes |
| --- | --- | --- | --- | --- | --- |
| Brainstorm PA2-SoftwareRequirementsSpecification-Plan | Whole team | 26/10/2026 |  | 100 | NONE |
| 2.1.1 Introduction: purpose, scope & glossary | Nguyễn Đại Phúc | 26/10/2026 |  | 100 | NONE |
| 2.1.2 Problem Statement (elaborated from PA1) | Nguyễn Đại Phúc | 26/10/2026 |  | 100 | NONE |
| 2.1.3 Stakeholders | Huỳnh Mạnh Tú | 26/10/2026 |  | 100 | NONE |
| 2.2.1 Functional Requirements | Huỳnh Mạnh Tú | 26/10/2026 |  | 100 | NONE |
| 2.2.2 Non-Functional Requirements | Nguyễn Đại Phúc | 26/10/2026 |  | 100 | NONE |
| 2.2.3 Domain Requirements and Business Rules | Lê Trọng Hiếu | 26/10/2026 |  | 100 | NONE |
| 2.2.4 Acceptance Criteria (Given/When/Then) | Phan Phú Trọng | 26/10/2026 |  | 70 | Move to Week 5 |
| Review: 2.1.1, 2.1.3, 2.2.2, 2.2.3 | Trần Duy Khang | 27/10/2026 |  | 100 | NONE |
| Review: 2.1.2 | Lê Trọng Hiếu | 27/10/2026 |  | 100 | NONE |
| Review: 2.2.1 | Lê Trọng Hiếu | 27/10/2026 |  | 100 | NONE |

## Plan for Next Week

| WBS / task | Owner | Planned finish | Reviewer | Planned finish |
| --- | --- | --- | --- | --- |
| 2.2.4 Acceptance Criteria (Given/When/Then) | Phan Phú Trọng | 29/10/2026 | Trần Duy Khang | 30/10/2026 |
| 2.3.1 Use Case Model: diagram, actors, use case list | Huỳnh Mạnh Tú | Friday 30/10/2026 20h00 | Lê Trọng Hiếu | Saturday 31/10/2026 10h00 |
| 2.3.2 Use case specifications: booking, cancellation, calendar, rules | Huỳnh Mạnh Tú | Sunday 1/11/2026 18h00 | Phan Phú Trọng | Monday 2/11/2026 10h00 |
| 2.3.3 Use case specifications: auth, court management, front desk | Phan Phú Trọng | Sunday 1/11/2026 18h00 | Nguyễn Đại Phúc | Monday 2/11/2026 10h00 |
| 2.4.1 Prototype / Mockups (Figma) | Trần Duy Khang | Monday 2/11/2026 14h00 | Nguyễn Đại Phúc | Monday 2/11/2026 17h00 |
| 2.5.1 Requirements Traceability Matrix | Lê Trọng Hiếu | Monday 2/11/2026 21h00 | Huỳnh Mạnh Tú | Tuesday 3/11/2026 9h00 |
| 2.5.2 Requirements Review | Phan Phú Trọng | Tuesday 3/11/2026 17h00 | Nguyễn Đại Phúc | Wednesday 4/11/2026 9h00 |
| 2.6.1 AI Usage Log | Whole team | Wednesday 4/11/2026 13h00 | Huỳnh Mạnh Tú | Wednesday 4/11/2026 15h00 |
| 2.6.2 Member Contribution, integration & submission | Lê Trọng Hiếu | Wednesday 4/11/2026 |  |  |

## Issues and Risks

None

## Meeting Minutes

| Member | Present | Done since last meeting | Next | Blockers |
| --- | --- | --- | --- | --- |
| 24127168 | YES | Review: 2.1.2 Review 2.2.1 | 2.5.1 Requirements Traceability Matrix 2.6.2 Member Contribution, integration & submission | NONE |
| 24127577 | YES | Review: 2.2.4 | 2.3.1 Use Case Model: diagram, actors, use case list 2.3.2 Use case specifications: booking, cancellation, calendar, rules | NONE |
| 24127183 | YES | Review: 2.2.2 | 2.4.1 Prototype / Mockups (Figma) | NONE |
| 24127500 | YES | 2.2.2 Non-Functional Requirements | Review: 2.3.3, 2.4.1, 2.5.2 | NONE |
| 23127134 | YES |  | 2.3.3 Use case specifications: auth, court management, front desk 2.5.2 Requirements Review | NONE |

## Metrics

| Metric | This week | Total |
| --- | --- | --- |
| Tasks completed | 10 | 9 |
| Commits | 3 | 3 |
| Pull requests merged / reviewed | 3 | 3 |
| Open defects (PA5) | 0 | 0 |